## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	SSAD48
PROJECT NAME	Web application for Text mining and storage of clinical data
PROJECT MENTOR (sponsor)	Kusuma Talluri ; Surya Nanduri
TEAM MEMBERS	Aniket Shrimal
	Aamir Farhan
	Lakshmee Sravya

## Status
PROJECT NUMBER	SSAD48
PROJECT NAME	Web application for Text mining and storage of clinical data
PROJECT MENTOR (sponsor)	Kusuma Talluri ; Surya Nanduri

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 14- August 20)
Fix meeting with client	Coordination	Aamir	0.5	0.25	Done		0.25	100
GIT Repository setup	Preparation	Aniket	1	1.5	Done		-0.5	33.3333333333
Client meeting	Coordination	Aamir	1.5	0.75	Done	first introductory meet	0.75	100
Identify role owners	Preparation	Lakshmee	1	0.6	Done	think about role & reponsibility distribution	0.4	66.6666666667
Team Meeting	Coordination	Lakshmee	1.5	2	Done	Discuss about points dicuss in meeting with client	-0.5	25
Status tracker	Documentation	Aniket	1	0.75	Done		0.25	33.3333333333
Week 2 (August 21 - August 27)
Fix meeting with client	Coordination	Aamir	0.4	0.25	Done		0.15	60
Develop questions for requirements elicitation	Documentation	Lakshmee	2	1.5	Done	Make sure scoping questions are included	0.5	33.3333333333
Client meeting	Coordination	Aniket	1.5	1	Done	Meeting with TA and client	0.5	50
Team Meeting	Coordination	Aniket	1	1.5	Done	Discuss about requirements of project	-0.5	33.3333333333
Learn Text mining through NLP	Preparation	Aniket	10		Planned	Specified by client in meeting
Synopsis	Preparation	Aamir	1	1.5	Done	Project Synopsis
Status tracker	Documentation	Lakshmee	0.8	0.5	Done		0.3	60

Week 3 (August 28 – September 3)
Learn Text mining through NLP	Preparation	Aamir	10		Ongoing
Team Meeting	Coordination	Aniket	1.5	1	Done		0.5	50
Conference call with client	Coordination	Aamir	0.5	0.3	Done	Client discuss about nlp and how to learn it	0.2	66.6666666667
Status tracker	Documentation	Lakshmee	0.6	0.4	Done		0.2	50
Week 4 (September 4 - September 10)
Searched for text mining techniques	Preparation	Aniket	2	3	Done	Python tools for text mining were explored	-1	33.3333333333
Reading about Apache Solr	Preparation	Aamir	2	3	Done	Apache Solr uses server based text mining techniques	-1	33.3333333333
Collection of data from client	Preparation	Lakshmee	0.5	0.5	Done	Links to sources for clinical trials
Minutes of Meeting updated	Coordination	Lakshmee	0.5	1	Done
Week 5 (September 11 – September 17)
Fixed meeting with the client	Coordination	Aamir	1	1	Done		0	0
Got documentations evaluated	Coordination	All	1	1	Done	TA evaluated the Project Plan, Status Tracker and other documents	0	0
Explored Python NLP tools	Preparation	Aniket	2	2.5	Done		-0.5	20
Week 6 (September 18 – September 25)
Explored webscraping	Preparation	Aniket	2	2.5	Done		-0.5	20
Meeting with the client	Coordination	All	2	2	Done
Test Plan	Documentation	Lakshmee	2	1.5	Done		0.5	33.3333333333
Explored the database given	Preparation	Aamir	2	2.5	Done		-0.5	20
Week 7 (September 26 – October 3)
Designed the login page	Development	Aniket	2	1.5	Done		0.5	33.3333333333
Designed the signup	Development	Lakshmee	2	1.5	Done		0.5	33.3333333333
Designed the signup frontend	Development	Aamir	2	2	Done		0	0
Status tracker	Documentation	Lakshmee	0.8	0.5	Done		0.3	60
Week 8 (October4 – October 11)
Status tracker	Documentation	Lakshmee	0.8	0.5	Done		0.3	60
Video recording and editing	Preparation	Aamir	2	2	Done
Prepared for R1	Preparation	All	3	3	Done		0	0
Week 8 (October 4 – October 11)
Studied Beautifulsoup	Development	Aamir	2	2	Done		0.5	33.3333333
Explored basics of selenium	Development	Lakshmee	2	2	Done		0.5	33.333333
Implementing browse/download feature	Development	Aniket	2	2	Done
Tried to fix web browser problem	Development	Aniket	2	2	Done		0.5	33.333333
Status tracker	Documentation	Lakshmee	0.8	0.5	Done		0.3	60
Week 9 (October 12 – October 19)
Examined the databases	Development	All	2	2	Done		0	0
Status tracker	Documentation	Lakshmee	0.8	0.5	Done		0.3	60
Week 10 (October 20 – October 27)
Solved web-browser problem	Development	Aniket	3	3	Done		0	0
Conference call with client	Coordination	Aamir	0.5	0.5	Done
Status tracker	Documentation	Lakshmee	0.8	0.5	Done		0.3	60
Week 11 (October 28 – November 4)
Search feature	Development	Aniket	2	2	Done		0	0
Changes in controller	Development	Aniket	2	2	Done		0	0
Updated all documents	Documentation	Aamir	2	2	Done		0	0
Status tracker	Documentation	Lakshmee	0.5	0.5	Done		0	0
Week 11 (October 4 – November 11)
Download feature and image	Development	Aniket	2	2	Done		0	0
User main page and frontend	Development	Aamir	2	2	Done		0	0
Status tracker and R2 presentation	Documentation	Lakshmee	2	2	Done		0	0